## Bugs
# | Bug | State | Prio | Data | Desription
1 | Bug rerquest states should be translated | Review | Middle | 2020-11-23 | Localization file added in common
2 | Move buttons on the bottom in the list | Review | Low | 2020-11-23
3 | Absent sorting | Review | High | 2020-11-23
4 | Group filter elements | InProgress | Low | 2020-11-23
5 | Add icons | Review | Low | 2020-11-23
6 | Return to the list from item page | Review | High | 2020-11-23 | Added button at the bottom of entity page
7 | Add tabulation to the iltem data | New | Middle | 2020-11-23
8 | Group buttons on the item page | New | Low | 2020-11-23
9 | Add info panel (probably on the top) | Review | High | 2020-11-23
10 | Approver doesn't appear on item page after approve | New | Middle | 2021-01-13
11 | Executor doesn't appear on itempage after approving | New | Middle | 2021-01-13
12 | Executor can not change price field after approving | New | Low | 2021-01-13
13 | Add postponed button for director and fin director | New | Middle | 2021-01-13
14 | Add declined button for director and approver | New | Middle | 2021-01-13
15 | Add comments on item page | New | Middle | 2021-01-13
16 | FinDirector can not change execution deadline date field after approving | New | Low | 2021-01-13
17 |  | New | Low
18 |  | New | Low
19 |  | New | Low
20 |  | New | Low
21 |  | New | Low
22 |  | New | Low
23 |  | New | Low
24 |  | New | Low
25 |  | New | Low
26 |  | New | Low
27 |  | New | Low
28 |  | New | Low
29 |  | New | Low
30 |  | New | Low
31 |  | New | Low

## States
New
InProgress
Review
Done

## Priority
Low
Middle
High
Critical